## Sheet1
Contingency Plan Sample
Organization Name: Community Health Initiative
Organization Mission: To improve community health outcomes through education, access to care, and advocating for health equity.
Mission Drivers:
Health Services – provide health services to uninsured patients
Advocacy – advocate to government for increased health services access for unisured patients
Education – inform community about the impact of poor health care and lack of health care services
Plan Objectives:
Ensure essential services remain operational
Maintain communication with stakeholders
Minimize staff disruptions and layoffs
Identify alternative funding sources
Risk Assessment
Date | Driver | Risk Description | Potential Impact | Likelihood | Priority | Status | Triggering Conditions |  |  | Responsibility | Resource Requirements | Estimated Cost | Notes
|  | Sudden loss of funding | Reduced capacity to deliver programs/program termination | 60% | High |  | Receive notification letter |  |  |  |  | 50000
|  |  | Staff reductions | 50%
|  |  | Loss of stakeholder confidence | 40%
Risk Mitigation Strategies
Immediate Actions (Week 1) | [6 empty] | Timeline |  |  | Resources
Priority | Driver | Task (Action Item) | Key Performance Indicators (KPIs) | Phase | Assigned | Status | Start Date | Due Date | Duration | Resource requirements |  | Estimated Cost | Notes
1 |  | Assess Financial Impact | Reserve amount, liquidity, cash flow, run rate |  | ED/CFO/Board |  | 2025-04-15 | 2025-04-18 |  | Staff time
2 |  | Prioritize program delivery | # of patients impacted, cost of program delivery |  | Program Directors |  | 2025-04-15 | 2025-04-18 |  | Staff Time
3 |  | Communication | Communications to staff, board, other stakeholders |  | Comm. Director/ ED/Board |  | 2025-04-15 | 2025-04-18 |  | Staff Time
Short Term Actions (Weeks 2-3) | [6 empty] | Timeline |  |  | Resources
Priority | Driver | Task (Action Item) | Key Performance Indicators (KPIs) | Phase | Assigned | Status | Start Date | Due Date | Duration | Resource requirements |  | Estimated Cost | Notes
|  | Revise budget to reflect and financial dashboard based on financial assessment | Budget is revised and approved by the board
|  | Create plan for service delivery adaptations reflecting situation | Plan is complete and approved by the board, services are still being delivered in some form
|  | Create plan for staff changes based on financial assessment | Plan is complete and approved by the board
|  | Create communications plan | Staff, Board and Stakeholders are getting regular updates
Medium-Term Actions (3 - 5 Weeks) | [6 empty] | Timeline |  |  | Resources
Priority | Driver | Task (Action Item) | Key Performance Indicators (KPIs) | Phase | Assigned | Status | Start Date | Due Date | Duration | Resource requirements |  | Estimated Cost | Notes
Long-term Actions
Priority | Driver | Task (Action Item) | Key Performance Indicators (KPIs) | Phase | Assigned | Status | Start Date | Due Date | Duration | Resource requirements |  | Estimated Cost | Notes