ACTION PLANNING TEMPLATE

Sample Page

ACTION OUTCOME: XYZ Organization has more funding flexibility

Action: Secure a Line of Credit (LOC)

Success Indicator(s): XYZ has access to a $250,000 line of credit, LOC is secured by X/XX/XXXX

Conditions: Accurate and current financial statements, Loan Packet for banks, Board and staff engagement in process, Time

| Action Steps: | Deadline: | Estimated Cost: | Responsible: |
| --- | --- | --- | --- |
| - Board approval to seek LOC - Discuss need with Finance Committee for recommendation - Discuss need with Exec Committee for recommendation - Discuss need and present recommendation to Board for Approval - Board Approval - Create loan packet for potential lenders - Review current financial statements - Collect copy of audited financials - Collect 990 - Collect Article of Incorporation - Collect copy of By Laws - Research and identify potential lenders - Seek input from Board members on potential - Contact and engage potential lenders - Review Lender offers - Accept and Sign Lender Offer | - 2- 3 weeks - 2-3 weeks (done in parallel with #1) - 3 – 4 Weeks - 3 – 4 Weeks - 4-5 Weeks - 5-8 weeks | $0.00 $0.00 LOC closing costs and fees | - CFO - ED - Treasurer and Fin. Com. - President and Exec Com. - Board - CFO/Finance Staff - ED - CO, ED, Board - ED, CFO - ED, CFO, Fin. Comm, Exec Comm., Board - Board, President, Treasurer, ED |

ACTION OUTCOME:

Action:

Success Indicator(s):

Conditions:

| Action Steps: | Deadline: | Estimated Cost: | Responsibility: |
| --- | --- | --- | --- |
| 1. |  |  |  |

ACTION OUTCOME:

Action:

Success Indicator(s):

Conditions:

| Action Steps: | Deadline: | Estimated Cost: | Responsibility: |
| --- | --- | --- | --- |

ACTION OUTCOME:

Action:

Success Indicator(s):

Conditions:

| Action Steps: | Deadline: | Estimated Cost: | Responsibilty: |
| --- | --- | --- | --- |

ACTION OUTCOME:

ACTION:

Success Indicator(s):

Conditions:

| Action Steps: | Deadline: | Estimated Cost: | Responsibility: |
| --- | --- | --- | --- |

ACTION OUTCOME:

Action:

Success Indicator(s):

Conditions:

| Action Steps: | Deadline: | Estimated Cost: | Responsibility: |
| --- | --- | --- | --- |

ACTION OUTCOME:

Action:

Success Indicator(s):

Conditions:

| Action Steps: | Deadline: | Estimated Cost: | Responsibility: |
| --- | --- | --- | --- |